TERRAZZO

Taste Intelligence Engine

Technical Roadmap & Implementation Status

Updated March 2, 2026 | Confidential

Reflects actual codebase state across terrazzo-web and terrazzo-pipeline-worker

# Executive Summary

This document is a refreshed version of the Terrazzo Taste Intelligence Roadmap, updated to reflect the actual implementation state as of March 2026. It maps every original ticket to its current status (Done, Partial, or Not Started) and introduces new tickets discovered during implementation.

### Implementation Progress

| Phase 1: Taste Graph | Phase 2: Property Embeddings | Phases 3–5 | Overall |
| --- | --- | --- | --- |
| 7/10 done (70%) | 7/11 done (64%) | Not yet started | 14/52 done (27%) |

### Key Accomplishments (P0/P1)

- 34-dimensional taste vector computation for users and properties (8 domain + 26 signal features)

- pgvector-powered nearest-neighbor queries for user-to-user and user-to-property matching

- TasteNode/TasteEdge graph schema with full signal extraction and backfill pipeline

- 10-stage property enrichment pipeline (Google Places, reviews, editorial, Instagram, menu, awards, review intelligence, sustainability, sensory analysis, merge)

- Signal decay with 180-day half-life, taste trajectory analysis (REFINING/EXPANDING/SHIFTING/STABLE)

- Multi-modal onboarding: voice input, experience pool (Elo ranking), designer pool (mood boards)

- Profile refinement flow (/profile/refine) with gap detection for v2 fields

- 119 tests passing, TypeScript build green, both repos committed and pushed

### Critical Bugs Found & Fixed During Audit

- vectors.ts deprecated 2 of 8 domains: Rhythm and CulturalEngagement were deprecated from ALL_DOMAINS. They were previously included in property embeddings and user taste vectors but are no longer active. Fixed in commit 25533cd.

- Sensory analysis pipeline stage never built: stage_merge() had sensoryCues hardcoded to null. The entire sensory analysis LLM stage was missing. Built and integrated as stage_sensory_analysis().

# Phase 1: Proprietary Taste Graph

Timeline: Months 1–3 | Pillar: Deep Taste Intelligence

The taste graph foundation is largely complete. TasteNode/TasteEdge schema is deployed, signal extraction and backfill pipelines work end-to-end, pgvector is enabled with 34-dimensional taste vectors, and nearest-neighbor queries are functional. The main gaps are in higher-level analysis (contradiction co-occurrence, signal clustering) and replacing LLM-generated taste neighbors in the UI with real computed ones.

### Tickets

| ID | Ticket | Effort | Pri | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| TG-01 | Design TasteNode/TasteEdge Prisma schema | M | P0 | DONE | Full schema with decay columns, modality tracking |
| TG-02 | Migration: extract signals from User.allSignals into TasteNode | L | P0 | DONE | backfillUser() in backfill.ts, idempotent |
| TG-03 | Enable pgvector, add vector(34) column to User | S | P0 | DONE | Migration 20260227_add_taste_intelligence |
| TG-04 | Build taste vector computation (radarData + micro-signal hashes) | M | P0 | DONE | vectors.ts: 8 domain dims + 26 hash features |
| TG-05 | Nearest-neighbor query (cosine similarity) with index | M | P1 | DONE | findTasteNeighbors() via pgvector <=> operator |
| TG-06 | Build contradiction co-occurrence index | M | P1 | NOT STARTED | ContradictionNode table exists, no analysis code |
| TG-07 | Replace LLM-generated tasteNeighbors with real neighbors | S | P1 | PARTIAL | Query infra ready; discover route not yet rewired |
| TG-08 | Build signal clustering job (k-means/HDBSCAN) | L | P2 | NOT STARTED |  |
| TG-09 | Admin dashboard: visualize taste graph, clusters | M | P2 | PARTIAL | Only backfill-place-ids admin endpoint exists |
| TG-10 | Backfill pipeline: process all existing users | M | P0 | DONE | backfillAllUsers() + runFullBackfill() with Inngest |

### New Tickets Discovered

| ID | Ticket | Effort | Pri | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| TG-11 | Add HNSW index on User.tasteVector for production NN queries | S | P1 | NEW | Currently no explicit index; needed at scale |
| TG-12 | Taste vector recomputation job: re-embed users after profile changes | M | P1 | NEW | Vectors stale after refinement or behavioral updates |

# Phase 2: Property Embeddings

Timeline: Months 2–5 | Pillar: Place Intelligence as Editorial

Property embedding infrastructure is solid. The signal-to-vector pipeline maps enrichment signals to the same 34-dimensional space as user taste vectors, enabling direct cosine similarity. User-to-property and property-to-property queries are functional. The main gaps are in advanced embedding features (review intelligence via sentence transformers, CLIP visual embeddings) and operational tooling (scheduled refresh jobs, evaluation harness).

### Tickets

| ID | Ticket | Effort | Pri | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| PE-01 | Design property embedding schema: dimensions, storage | M | P0 | DONE | PlaceIntelligence.embedding vector(34) |
| PE-02 | Build signal-to-vector pipeline (computePropertyEmbedding) | L | P0 | DONE | vectors.ts: domain weights + hashed signals |
| PE-03 | Add pgvector column + HNSW index to PlaceIntelligence | S | P0 | PARTIAL | Column exists; HNSW index not explicitly created |
| PE-04 | Build user-to-property matching query (cosine similarity) | M | P0 | DONE | findSimilarProperties() + scoreWithVectors() |
| PE-05 | Build property-to-property similarity query | M | P1 | DONE | findSimilarPropertiesToProperty() |
| PE-06 | Integrate review intelligence into embeddings (sentence transformer) | L | P1 | NOT STARTED | Signals are hashed, not semantically embedded |
| PE-07 | Build embedding refresh job via Inngest | M | P1 | PARTIAL | Inngest client set up; no scheduled refresh function |
| PE-08 | Backfill embeddings for all PlaceIntelligence records | M | P0 | DONE | backfillAllPropertyEmbeddings() |
| PE-09 | Build taste-dimension slice queries for feed cards | M | P1 | PARTIAL | findPropertiesByDomain() exists, basic implementation |
| PE-10 | Evaluation harness: embedding vs. LLM-only recs | L | P1 | NOT STARTED |  |
| PE-11 | CLIP visual embeddings for property photos (stretch) | XL | P2 | NOT STARTED |  |

### New Tickets Discovered

| ID | Ticket | Effort | Pri | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| PE-12 | Create HNSW index on PlaceIntelligence.embedding | S | P1 | NEW | Needed for sub-100ms similarity queries at scale |
| PE-13 | Embedding dimension alignment: ensure User(34) and Place(34) match | S | P0 | NEW | Schema shows vector(32) on Place vs vector(34) on User — verify and align |

# Pipeline Enrichment (terrazzo-pipeline-worker)

The property enrichment pipeline has grown from the original 8 stages to 10 stages. All are implemented in server.py.

### Pipeline Stage Status

| # | Stage | Status | Notes |
| --- | --- | --- | --- |
| 1 | google_places | DONE | Core property data from Google Places API |
| 2 | scrape_reviews | DONE | Multi-source review aggregation |
| 3 | editorial_extraction | DONE | Editorial signals from curated sources |
| 4 | instagram_analysis | DONE | Visual and social signal extraction |
| 5 | menu_analysis | DONE | Food & drink identity from menu data |
| 6 | award_positioning | DONE | Award/recognition signal extraction |
| 7 | review_intelligence | DONE | Deep review analysis with sentiment themes |
| 9 | sustainability_analysis | DONE | P1: Environmental and social responsibility signals |
| 11 | sensory_analysis | DONE | P1: Light, sound, scent, texture cues (was missing, now built) |
| 12 | merge | DONE | Combines all stage outputs, deduplicates signals |

## P1 Infrastructure Additions (Not in Original Roadmap)

Several significant features were built during P1 that extend beyond the original 52-ticket roadmap. These support the v2 taste model and provide infrastructure that later phases depend on.

### Signal Decay (src/lib/signal-decay.ts)

Implements 180-day half-life exponential decay for signal confidence. Older signals contribute less to matching. Includes computeSignalAge(), decayConfidence(), isAgedOut(), and needsReprofiling() based on configurable thresholds. Integrated into taste-match.ts scoring.

### Taste Trajectory (src/lib/taste-trajectory.ts)

Analyzes how a user’s taste evolves over time. Detects four trajectory types: REFINING (deepening existing preferences), EXPANDING (broadening into new domains), SHIFTING (moving away from old preferences), STABLE (consistent taste). Used for adaptive recommendations and profile evolution insights.

### Multi-Modal Onboarding

- Voice input support with speech-to-text transcription and intelligent garbled-name correction

- Experience Pool (Phase 8): Elo-ranked pairwise comparisons of real properties to calibrate taste

- Designer Pool (Phase 9): Mood board selections for visual/aesthetic taste calibration

- 11 onboarding phases total with per-phase certainty tracking and cross-phase context memory

### Profile Refinement Flow (/profile/refine)

Gap detection system that identifies which v2 fields (sustainability, trajectory) are missing or default, surfaces only the relevant refinement phases, and re-synthesizes the profile on completion. Prevents re-asking questions the user has already answered.

### Database Schema Additions (v2)

- User model: 8 new columns (sustainability fields, taste trajectory, modality metadata)

- PlaceIntelligence model: 5 new columns (sensoryCues, sustainabilityScore, etc.)

- All existing users backfilled with default v2 values via direct SQL

# Phase 3: Collaborative Filtering

Timeline: Months 4–8 | Status: Not yet started | 10 tickets

Collaborative filtering depends on sufficient user interaction data. The infrastructure from Phases 1–2 (taste vectors, property embeddings) provides the warm-start priors. Event collection (BF-01–BF-03 from Phase 4) should begin soon to start accumulating the interaction data CF needs.

Prerequisite: Begin Phase 4 event collection in parallel so interaction data is accumulating while CF infrastructure is built.

### Tickets (unchanged from original roadmap)

| ID | Ticket | Effort | Pri | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| CF-01 | Design interaction event schema: types, weights, decay | M | P0 | NOT STARTED |  |
| CF-02 | Build interaction tracking: instrument discover, trip planner | L | P0 | NOT STARTED |  |
| CF-03 | Build interaction matrix materialization job (Inngest) | M | P0 | NOT STARTED |  |
| CF-04 | Implement ALS matrix factorization with taste-vector warm start | XL | P0 | NOT STARTED | Depends on TG-04 (done), PE-04 (done) |
| CF-05 | Build hybrid scoring: content + collaborative blend | L | P1 | NOT STARTED |  |
| CF-06 | Cold-start fallback (new user = content only) | M | P1 | NOT STARTED |  |
| CF-07 | A/B test framework: collaborative vs. content-only | L | P1 | NOT STARTED |  |
| CF-08 | Model retraining pipeline: weekly retrain via Inngest | M | P1 | NOT STARTED |  |
| CF-09 | Contradiction-aware collaborative patterns | L | P2 | NOT STARTED |  |
| CF-10 | Offline evaluation: precision/recall/NDCG | M | P1 | NOT STARTED |  |

# Phase 4: Behavioral Feedback Loops

Timeline: Months 3–6+ | Status: Not yet started | 11 tickets

The behavioral feedback loop is the primary mechanism for creating switching cost. Event collection (BF-01–BF-03) should be prioritized immediately as the data accumulation timeline is the bottleneck for both this phase and Phase 3.

### Tickets (unchanged from original roadmap)

| ID | Ticket | Effort | Pri | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| BF-01 | Design unified event schema (feed, place, trip, search) | M | P0 | NOT STARTED | Should start now — data accumulation is the bottleneck |
| BF-02 | Client-side event tracking SDK (React hooks) | L | P0 | NOT STARTED |  |
| BF-03 | Event ingestion API with batching and deduplication | M | P0 | NOT STARTED |  |
| BF-04 | Delta vector computation from interaction events | L | P0 | NOT STARTED |  |
| BF-05 | Incremental taste vector update with decay | L | P1 | NOT STARTED |  |
| BF-06 | Baseline/learned vector blending | M | P1 | NOT STARTED |  |
| BF-07 | Weekly full re-synthesis job | M | P1 | NOT STARTED |  |
| BF-08 | Feed card engagement tracking | M | P0 | NOT STARTED |  |
| BF-09 | Feed adaptation: weight cards by engagement | L | P1 | NOT STARTED |  |
| BF-10 | Taste evolution view: show profile shifts over time | M | P2 | NOT STARTED |  |
| BF-11 | Privacy controls: user data management | M | P1 | NOT STARTED |  |

# Phase 5: Grounded Generation

Timeline: Months 6–10 | Status: Not yet started | 10 tickets

Grounded generation is the capstone phase where the LLM becomes the editorial presentation layer on top of the recommendation engine, rather than the intelligence layer. This depends on Phases 1–4 being substantially complete.

Note: The discover route already has a scoreWithVectors() function that blends 60% vector scoring with 40% signal scoring. This is a partial foundation for GG-01/GG-02.

### Tickets (unchanged from original roadmap)

| ID | Ticket | Effort | Pri | Status | Notes |
| --- | --- | --- | --- | --- | --- |
| GG-01 | Candidate retrieval: top-K by embedding + collaborative score | L | P0 | NOT STARTED | scoreWithVectors() is early foundation |
| GG-02 | Scoring/ranking with configurable weight blend | L | P0 | NOT STARTED |  |
| GG-03 | Slot allocation: map candidates to feed card types | M | P0 | NOT STARTED |  |
| GG-04 | Restructure DISCOVER_SYSTEM_PROMPT for editorial-only generation | M | P0 | NOT STARTED |  |
| GG-05 | Build grounded discover API route | L | P0 | NOT STARTED |  |
| GG-06 | Diversity penalty in scoring | M | P1 | NOT STARTED |  |
| GG-07 | Precision@K and engagement metrics pipeline | M | P1 | NOT STARTED |  |
| GG-08 | Serendipity metric: engagement on stretch picks | M | P2 | NOT STARTED |  |
| GG-09 | A/B test: grounded vs. LLM-only generation | L | P0 | NOT STARTED |  |
| GG-10 | Recommendation explanation layer | M | P1 | NOT STARTED |  |

# Recommended Next Steps

### Immediate (This Week)

- Deploy pipeline worker to Railway with the new sensory analysis stage and re-enrich all 13 properties

- Push terrazzo-web (2 commits ahead) and verify production build

- Run npm test on local machine to confirm 119 tests pass with vector fixes

- Create HNSW indexes on User.tasteVector and PlaceIntelligence.embedding (PE-12, TG-11)

- Verify PE-13: embedding dimension alignment between User vector(34) and PlaceIntelligence vector(34)

### Short-Term (Next 2–4 Weeks)

- Complete TG-07: Wire real taste neighbors into discover route, replacing LLM-fabricated neighbors

- Build PE-07: Inngest-scheduled embedding refresh job for property re-embedding after pipeline runs

- Start BF-01–BF-03: Design event schema and begin collecting interaction data NOW (data accumulation is the bottleneck for Phases 3–4)

- Build TG-12: Taste vector recomputation trigger after profile refinement changes

### Medium-Term (Months 2–3)

- Phase 3 CF-01–CF-04: Collaborative filtering foundation (interaction matrix, ALS with warm start)

- Phase 4 BF-04–BF-06: Delta vectors from behavioral data, baseline/learned blending

- TG-06: Contradiction co-occurrence analysis

- PE-06: Explore sentence-transformer integration for richer review embeddings

# Appendix: Full Ticket Summary

52 original tickets + 3 new tickets = 55 total

| Category | Done | Partial | Not Started | New |
| --- | --- | --- | --- | --- |
| Phase 1: Taste Graph | 6 | 2 | 2 | 2 |
| Phase 2: Property Embeddings | 5 | 3 | 3 | 2 |
| Phase 3: Collaborative | 0 | 0 | 10 | 0 |
| Phase 4: Behavioral | 0 | 0 | 11 | 0 |
| Phase 5: Grounded Gen | 0 | 0 | 10 | 0 |
| TOTAL | 11 | 5 | 36 | 4 |

— End of Document —